## Sheet1
SCHOOL OF COMPUTER ENGINEERING Summer Internship Program 2023
Name : Sarvesh Shingare |  |  | Company Name: Grouply
PRN : 202101050031 |  |  | Industry Mentor: Onkar Kadam
Phone number: 7020800359 |  |  | Industry Project Title: E-commerce website
Institute Mentor/guide: Mrs Smita Kulkarni |  |  | Industry Mentor mail and Contact: onkar@grouply.in 83780 40043
HR mail and Contact: hr@grouply.in 7559499399
| Week1-2 | Week 3-4 | Week 5-6 | Week 7-8
Work Planned | Week 1: Understand the company's frontend development workflow, focusing on React and Tailwind CSS integration. Build foundational UI components, such as Button, Input Field, and Navbar, adhering to component structure guidelines and styling conventions. Week 2: Refactor components to align with the company's design system using Tailwind CSS. Develop advanced UI components such as Card, Form, and Modal with responsive behavior and real-time form validation. Focus on integrating React state management and dynamic interactions for user input handling.
Work Completed | Week 1: Successfully developed basic UI components: Button Component: A reusable button with customizable props for different states and styles. Input Field Component: A dynamic input field with form validation functionality. Navbar Component: Responsive navigation bar that adapts to both mobile and desktop views. Gained familiarity with the existing codebase and its component structure. Week 2: Integrated Tailwind CSS, refactoring the existing components for faster, more efficient styling. Completed more advanced components: Card Component: A dynamic and reusable card supporting various props, refactored with Tailwind for responsiveness. Form Component: A form with real-time validation and responsive feedback. Modal Component: Smooth and responsive modal for user interaction. Ensured all components were responsive, tested across different devices (mobile, tablet, desktop).
Tech Stack worked on | React: Core library for building UI components. Tailwind CSS: Utility-first CSS framework used for faster styling and responsive design. Styled Components: For dynamic, scoped CSS-in-JS styling within React components.
Major Contribution(S) | Week 1: Developed core UI components (Button, Input Field, Navbar) that serve as foundational elements for the project. Ensured consistent adherence to company guidelines for React component structure and styling. Week 2: Refactored components using Tailwind CSS, reducing custom CSS and improving responsiveness. Developed advanced, reusable components like the Card Component and Form Component, enhancing the UI. Implemented Modal Component with smooth animations and responsive behavior, enhancing user experience. Assisted in improving the overall scalability and maintainability of the frontend codebase.
Achivements | Company Familiarization: Successfully navigated internal resources, project goals, and participated in team meetings to gain clarity on the company’s development environment. Tailwind CSS Integration: Streamlined the styling process by refactoring the existing components with Tailwind CSS. Utilized utility-first classes for faster, more responsive UI development
your Remarks on project progress | Foundation in Frontend Development: Built a strong foundation in React and Tailwind CSS, gaining experience in creating both simple and complex UI components. Navigating the Codebase: Initially faced challenges with understanding the flow of data between components, but successfully overcame them through exploration and team support. Tailwind CSS Mastery: Tailwind CSS posed a learning curve but proved invaluable for efficient styling and responsive design. Frequent references to documentation helped solidify understanding.
Institute Guide Remarks