## Sheet1
SCHOOL OF COMPUTER ENGINEERING Summer Internship Program 2023
Name : Sarvesh Shingare |  |  | Company Name: Grouply
PRN : 202101050031 |  |  | Industry Mentor: Onkar Kadam
Phone number: 7020800359 |  |  | Industry Project Title: E-commerce website
Institute Mentor/guide: Mrs Smita Kulkarni |  |  | Industry Mentor mail and Contact: onkar@grouply.in 83780 40043
HR mail and Contact: hr@grouply.in 7559499399
| Week1-2 | Week 3-4 | Week 5-6 | Week 7-8
Work Planned | Week 1: Understand the company's frontend development workflow, focusing on React and Tailwind CSS integration. Build foundational UI components, such as Button, Input Field, and Navbar, adhering to component structure guidelines and styling conventions. Week 2: Refactor components to align with the company's design system using Tailwind CSS. Develop advanced UI components such as Card, Form, and Modal with responsive behavior and real-time form validation. Focus on integrating React state management and dynamic interactions for user input handling. | Week 3: Implemented conditional rendering based on user states (e.g., authenticated vs. guest users). Enhance UX with loading indicators, error handling, and reusable components for data presentation. Week 4: Focus on state management using the React Context API for handling global state. Develop additional UI elements, including a responsive Dashboard Component, Pagination Component, and reusable Modal Component. Optimize the performance of the frontend by reducing unnecessary re-renders. | Week 5: Convert Figma UI designs into functional, pixel-perfect React components. Focus on creating reusable components (buttons, input fields, icons) that align with the company's design standards and are responsive across different devices. Week 6: Continue developing small components from the Figma design and ensure that all components are responsive. Document the company’s frontend development processes, including component structure, styling best practices, and state management guidelines. | Convert the design of the company's e-commerce website into React components, ensuring modularity and responsiveness. Redesign certain elements of the website within the company’s branding guidelines to improve the user experience. Adapt to an existing codebase provided by the company and integrate new features without disrupting its functionality. Focus on optimizing performance and ensuring that key features, such as product listings, shopping cart, and checkout, provide a smooth user experience.
Work Completed | Week 1: Successfully developed basic UI components: Button Component: A reusable button with customizable props for different states and styles. Input Field Component: A dynamic input field with form validation functionality. Navbar Component: Responsive navigation bar that adapts to both mobile and desktop views. Gained familiarity with the existing codebase and its component structure. Week 2: Integrated Tailwind CSS, refactoring the existing components for faster, more efficient styling. Completed more advanced components: Card Component: A dynamic and reusable card supporting various props, refactored with Tailwind for responsiveness. Form Component: A form with real-time validation and responsive feedback. Modal Component: Smooth and responsive modal for user interaction. Ensured all components were responsive, tested across different devices (mobile, tablet, desktop). | Week 3:Dynamic Rendering: Created reusable card components to display dynamic content such as user or product data. Introduced pagination for handling large datasets. UX Enhancements: Added loading indicators and error handling to enhance the user experience using Tailwind CSS. Conditional Rendering: Implemented conditional rendering based on user states using React’s useContext. Developed dynamic form components that adjust based on user input. Week 4: State Management: Implemented React Context API for efficient global state management without external libraries like Redux. Ensured smooth data flow across deeply nested components. Dashboard Component: Built a responsive Dashboard Component that organizes data in a clean, modern layout. | Week 5: Figma to React Conversion: Successfully converted UI designs from Figma into React components while ensuring pixel-perfect accuracy. Components were built to reflect the design layout, spacing, typography, and color scheme exactly as specified. Component Development: Created several small, reusable components (buttons, input fields, icons) that could be used across multiple parts of the application. These components were tested for responsiveness and accuracy, ensuring they scaled appropriately across different screen sizes. Week 6: Responsiveness and Modularity: Ensured that all developed components followed responsive design principles, adapting fluidly to different devices such as mobile, tablet, and desktop. Documentation: Compiled detailed documentation outlining the frontend development process. This included component structuring, styling conventions, naming standards, and state management practices used in the project. | E-Commerce Website Conversion: Successfully converted the design into functional React components, building core pages like Product Listings, Shopping Cart, and Checkout. Responsive Design: Implemented responsive design to ensure the website works seamlessly across various devices. Redesign Flexibility: Used the flexibility provided by the company to redesign UI elements, focusing on improving the website’s overall visual appeal and user experience while staying aligned with the company’s branding. Codebase Adaptation: Adapted to the existing codebase, overcoming initial challenges in navigating the structure and style. Gradually contributed by integrating new components and features. Component Optimization: Refactored React components to reduce unnecessary re-renders, optimizing state management for better performance and ensuring that components were modular and reusable.
Tech Stack worked on | React , Tailwinds CSS | React ,Tailwind CSS ,React Context API | React ,Tailwind CSS ,React Context API, Figma | React ,Tailwind CSS ,React Context API, Figma
Major Contribution(S) | Week 1: Developed core UI components (Button, Input Field, Navbar) that serve as foundational elements for the project. Ensured consistent adherence to company guidelines for React component structure and styling. Week 2: Refactored components using Tailwind CSS, reducing custom CSS and improving responsiveness. Developed advanced, reusable components like the Card Component and Form Component, enhancing the UI. Implemented Modal Component with smooth animations and responsive behavior, enhancing user experience. Assisted in improving the overall scalability and maintainability of the frontend codebase. | Week 3: Created conditional rendering for different user states, enhancing interactivity and overall user experience. Developed a reusable card component for displaying various types of data, improving scalability. Week 4: Implemented efficient global state management using the React Context API, improving the overall scalability and data flow between components. Built responsive UI elements like the Dashboard Component and Pagination Component, enhancing user navigation and data organization. | Figma to React Conversion: Converted static Figma designs into interactive, fully responsive React components, adhering to pixel-perfect accuracy and ensuring design consistency. Reusable Component Development: Built modular and reusable components, such as buttons, input fields, and icons, that can be utilized across different sections of the application. This modularity contributes to the scalability of the project and helps maintain uniform design standards. Documentation: Provided comprehensive documentation on the frontend development process, making it easier for future developers to understand the company’s React practices, component structuring, and styling guidelines. This documentation is intended to improve team collaboration and the onboarding process for new developers. | E-Commerce Website Development: Converted the company’s e-commerce website design into React components while ensuring it remained responsive and visually aligned with modern UI/UX practices. Redesign of UI Elements: Leveraged the creative freedom to redesign certain aspects of the site, significantly improving user experience and aesthetics. Codebase Integration: Successfully adapted to the company’s legacy codebase, integrating new components without disrupting the existing functionality. Performance Optimization: Refactored components to enhance performance, ensuring smoother user interactions and better state management.
Achivements | Company Familiarization: Successfully navigated internal resources, project goals, and participated in team meetings to gain clarity on the company’s development environment. Tailwind CSS Integration: Streamlined the styling process by refactoring the existing components with Tailwind CSS. Utilized utility-first classes for faster, more responsive UI development | State Management: Successfully managed global state across components using React Context API, avoiding the need for external libraries while maintaining scalability and simplicity. Component Development: Developed new UI elements such as the Dashboard Component, Pagination Component, and Modal Component, improving the user experience. | Figma to React Conversion: Converted static UI designs into pixel-perfect, fully responsive React components. Ensured all components adhered to the company’s design principles, maintaining consistency across the application. Reusable Components: Developed small, reusable components, such as buttons and input fields, that align with the design system and are scalable across various parts of the application. | Responsive E-Commerce Pages: Built essential e-commerce pages such as Product Listings, Shopping Cart, and Checkout, all fully responsive across devices. Improved UX/UI: Redesigned specific elements of the website, focusing on modernizing the interface while maintaining company branding. Codebase Adaptation: Overcame the challenge of adapting to a pre-existing codebase, making meaningful contributions to the project. Performance Improvements: Optimized components to reduce unnecessary re-renders and improve overall performance.
your Remarks on project progress | Foundation in Frontend Development: Built a strong foundation in React and Tailwind CSS, gaining experience in creating both simple and complex UI components. Navigating the Codebase: Initially faced challenges with understanding the flow of data between components, but successfully overcame them through exploration and team support. Tailwind CSS Mastery: Tailwind CSS posed a learning curve but proved invaluable for efficient styling and responsive design. Frequent references to documentation helped solidify understanding. | Component Reusability and Performance: A strong focus on developing reusable components has improved the maintainability of the frontend. The use of React.memo has effectively optimized performance. Challenges in Asynchronous Data Handling: Managing asynchronous data and state flow between components presented some initial difficulties but was resolved through careful refactoring and optimization techniques. Progress Toward Scalability. | UI and Component Development: Converted Figma designs into fully functional React components, ensuring they were pixel-perfect, responsive, and reusable across the application, enhancing scalability and maintainability. Challenges in Design Interpretation: Clarified some dynamic behaviors and hover effects with the design team, successfully implementing the components as intended. Documentation Contribution: Created detailed documentation to aid future developers, providing clear guidelines on component structure, styling, and state management for consistent project development. | Adapting to Legacy Code: Adapting to the existing codebase was initially challenging but ultimately rewarding. I learned how to navigate and contribute to legacy code while introducing new features and improvements. Balancing Creativity with Business Needs: The flexibility in redesign allowed me to bring in creative ideas, but I had to ensure these aligned with the company's branding and project requirements. Overall Progress: The work completed during Weeks 7 and 8 significantly advanced the development of the company’s e-commerce website.
Institute Guide Remarks